## Sprint 3-4
Iteration Number:
|  |  | Expected Total effort: |  |  |  | 112
|  |  | Days In Sprint: |  |  |  | 4
Burndown Chart
User Stories |  |  | Days (Points Completed) | [19 empty] | Remaining
Sprint Backlog Items | Done by | Beginning Balance | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | Task Balance | Percentage Completed
User Story 1 - RF1.1 | Team Member Name | 6 | Days (Points Completed) 1: 3; Days (Points Completed) 2: 3 | 0 | 100% | 1
User Story 1 - RF1.2 | Team Member Name | 6 | Days (Points Completed) 1: 3; Days (Points Completed) 2: 3 | 0 | 100% | 1
User Story 1 - RF1.6 | Team Member Name | 5 | Days (Points Completed) 1: 3; Days (Points Completed) 2: 2 | 0 | 100% | 1
User Story 5 - RF2.1 | Team Member Name | 5 | Days (Points Completed) 2: 1; Days (Points Completed) 3: 4 | 0 | 100% | 1
User Story 5 - RF2.2 | Team Member Name | 5 | Days (Points Completed) 3: 1; Days (Points Completed) 4: 4 | 0 | 100% | 1
User Story 5 - RF2.3 | Team Member Name | 5 | Days (Points Completed) 3: 2; Days (Points Completed) 4: 3 | 0 | 100% | 1
User Story 5 - RF2.4 | Team Member Name | 5 | Days (Points Completed) 2: 1; Days (Points Completed) 3: 4 | 0 | 100% | 1
User Story 5 - RF2.5 | Team Member Name | 5 | Days (Points Completed) 2: 2; Days (Points Completed) 3: 1; Days (Points Completed) 4: 2 | 0 | 100% | 1
User Story 5 - RF2.6 | Team Member Name | 5 | Days (Points Completed) 2: 1; Days (Points Completed) 3: 1; Days (Points Completed) 4: 3 | 0 | 100% | 1
User Story 6 - RF2.2 | Team Member Name | 5 | Days (Points Completed) 2: 1; Days (Points Completed) 3: 4 | 0 | 100% | 1
User Story 6 - RF2.3 | Team Member Name | 5 | Days (Points Completed) 2: 2; Days (Points Completed) 3: 1; Days (Points Completed) 4: 2 | 0 | 100% | 1
User Story 6 - RF2.4 | Team Member Name | 5 | Days (Points Completed) 2: 1; Days (Points Completed) 3: 1; Days (Points Completed) 4: 3 | 0 | 100% | 1
User Story 6 - RF2.5 | Team Member Name | 5 | Days (Points Completed) 2: 1; Days (Points Completed) 3: 4 | 0 | 100% | 1
User Story 6 - RF2.6 | Team Member Name | 5 | Days (Points Completed) 2: 2; Days (Points Completed) 3: 2; Days (Points Completed) 4: 1 | 0 | 100% | 1
User Story 9 - RF16.1 | Team Member Name | 5 | Days (Points Completed) 3: 5 | 0 | 100% | 1
User Story 9 - RF16.2 | Team Member Name | 5 | Days (Points Completed) 3: 2; Days (Points Completed) 4: 3 | 0 | 100% | 1
User Story 9 - RF16.3 | Team Member Name | 5 | Days (Points Completed) 3: 2; Days (Points Completed) 4: 3 | 0 | 100% | 1
User Story 9 - RF16.4 | Team Member Name | 5 | Days (Points Completed) 3: 5 | 0 | 100% | 1
User Story 9 - RF16.5 | Team Member Name | 5 | Days (Points Completed) 3: 3; Days (Points Completed) 4: 2 | 0 | 100% | 1
User Story 9 - RF16.7 | Team Member Name | 5 | Days (Points Completed) 3: 2; Days (Points Completed) 4: 3 | 0 | 100% | 1
User Story 9 - RF16.8 | Team Member Name | 5 | Days (Points Completed) 3: 5; Days (Points Completed) 4: 0 | 0 | 100% | 1
User Story 9 - RF16.9 | Team Member Name | 5 | Days (Points Completed) 3: 2; Days (Points Completed) 4: 3 | 0 | 100% | 1
User Story 2 - RF1.3 | Team Member Name | 0 | [20 empty] | 0
User Story 2 - RF1.4 | Team Member Name | 0 | [20 empty] | 0
User Story 3 - RF1.5 | Team Member Name | 0 | [20 empty] | 0
User Story 4 - RF1.7 | Team Member Name | 0 | [20 empty] | 0
User Story 7 - RF2.7 | Team Member Name | [21 empty] | 0
User Story 8 - RF2.8 | Team Member Name | [21 empty] | 0
User Story 10 - RF3.1 | Team Member Name | [21 empty] | 0
User Story 10 - RF3.2 | Team Member Name | [21 empty] | 0
User Story 10 - RF3.3 | Team Member Name | [21 empty] | 0
User Story 10 - RF3.4 | Team Member Name | [21 empty] | 0
User Story 10 - RF4.1 | Team Member Name | [21 empty] | 0
User Story 10 - RF4.2 | Team Member Name | [21 empty] | 0
User Story 10 - RF4.3 | Team Member Name | [21 empty] | 0
User Story 10 - RF4.4 | Team Member Name | [21 empty] | 0
User Story 10 - RF4.5 | Team Member Name | [21 empty] | 0
User Story 10 - RF5.1 | Team Member Name | [21 empty] | 0
User Story 10 - RF5.2 | Team Member Name | [21 empty] | 0
User Story 10 - RF5.3 | Team Member Name | [21 empty] | 0
User Story 10 - RF5.4 | Team Member Name | [21 empty] | 0
User Story 10 - RF6.1 | Team Member Name | [21 empty] | 0
User Story 10 - RF6.2 | Team Member Name | [21 empty] | 0
User Story 10 - RF6.3 | Team Member Name | [21 empty] | 0
User Story 10 - RF6.4 | Team Member Name | [21 empty] | 0
User Story 11 - RF17.1 | Team Member Name | [21 empty] | 0
User Story 11 - RF17.2 | Team Member Name | [21 empty] | 0
User Story 11 - RF17.3 | Team Member Name | [21 empty] | 0
User Story 11 - RF17.4 | Team Member Name | [21 empty] | 0
User Story 12 - RF7.1 | Team Member Name | [21 empty] | 0
User Story 12 - RF7.4 | Team Member Name | [21 empty] | 0
User Story 13 - RF7.2 | Team Member Name | [21 empty] | 0
User Story 13 - RF7.3 | Team Member Name | [21 empty] | 0
User Story 14 - RF19.1 | Team Member Name | [21 empty] | 0
User Story 14 - RF19.2 | Team Member Name | [21 empty] | 0
User Story 14 - RF19.3 | Team Member Name | [21 empty] | 0
User Story 14 - RF19.4 | Team Member Name | [21 empty] | 0
User Story 15 - RF18.1 | Team Member Name | [21 empty] | 0
User Story 15 - RF18.2 | Team Member Name | [21 empty] | 0
User Story 15 - RF18.3 | Team Member Name | [21 empty] | 0
User Story 15 - RF18.4 | Team Member Name | [21 empty] | 0
User Story 16 - RF20.1 | Team Member Name | [21 empty] | 0
User Story 16 - RF20.2 | Team Member Name | [21 empty] | 0
User Story 16 - RF20.3 | Team Member Name | [21 empty] | 0
User Story 16 - RF20.4 | Team Member Name | [21 empty] | 0
User Story 17 - RF20.5 | Team Member Name | [21 empty] | 0
User Story 17 - RF20.7 | Team Member Name | [21 empty] | 0
User Story 18 - RF20.6 | Team Member Name | [21 empty] | 0
User Story 19 - RF8.1 | Team Member Name | [21 empty] | 0
User Story 19 - RF8.2 | Team Member Name | [21 empty] | 0
User Story 19 - RF8.3 | Team Member Name | [21 empty] | 0
User Story 19 - RF8.4 | Team Member Name | [21 empty] | 0
User Story 20 - RF9.1 | Team Member Name | [21 empty] | 0
User Story 21 - RF9.4 | Team Member Name | [21 empty] | 0
User Story 22 - RF9.2 | Team Member Name | [21 empty] | 0
User Story 22 - RF9.3 | Team Member Name | [21 empty] | 0
User Story 23 - RF10.1 | Team Member Name | [21 empty] | 0
User Story 23 - RF10.2 | Team Member Name | [21 empty] | 0
User Story 23 - RF10.3 | Team Member Name | [21 empty] | 0
User Story 23 - RF10.4 | Team Member Name | [21 empty] | 0
User Story 24 - RF11.1 | Team Member Name | [21 empty] | 0
User Story 24 - RF11.2 | Team Member Name | [21 empty] | 0
User Story 24 - RF11.3 | Team Member Name | [21 empty] | 0
User Story 24 - RF11.4 | Team Member Name | [21 empty] | 0
User Story 24 - RF11.5 | Team Member Name | [21 empty] | 0
User Story 24 - RF11.6 | Team Member Name | [21 empty] | 0
User Story 24 - RF11.7 | Team Member Name | [21 empty] | 0
User Story 25 - RF12.1 | Team Member Name | [21 empty] | 0
User Story 26 - RF12.1 | Team Member Name | [21 empty] | 0
User Story 26 - RF12.2 | Team Member Name | [21 empty] | 0
User Story 26 - RF12.3 | Team Member Name | [21 empty] | 0
User Story 26 - RF12.4 | Team Member Name | [21 empty] | 0
User Story 27 - RF13.1 | Team Member Name | [21 empty] | 0
User Story 28 - RF13.2 | Team Member Name | [21 empty] | 0
User Story 28 - RF13.3 | Team Member Name | [21 empty] | 0
User Story 28 - RF13.5 | Team Member Name | [21 empty] | 0
User Story 28 - RF13.6 | Team Member Name | [21 empty] | 0
User Story 29 - RF13.4 | Team Member Name | [21 empty] | 0
User Story 30 - RF14.1 | Team Member Name | [21 empty] | 0
User Story 31 - RF14.1.1 | Team Member Name | [21 empty] | 0
User Story 31 - RF14.1.2 | Team Member Name | [21 empty] | 0
User Story 31 - RF14.1.3 | Team Member Name | [21 empty] | 0
User Story 31 - RF14.1.5 | Team Member Name | [21 empty] | 0
User Story 31 - RF14.1.6 | Team Member Name | [21 empty] | 0
User Story 32 - RF14.2 | Team Member Name | [21 empty] | 0
User Story 32 - RF14.2.1 | Team Member Name | [21 empty] | 0
User Story 32 - RF14.2.2 | Team Member Name | [21 empty] | 0
User Story 32 - RF14.2.3 | Team Member Name | [21 empty] | 0
User Story 32 - RF14.2.4 | Team Member Name | [21 empty] | 0
User Story 32 - RF14.2.5 | Team Member Name | [21 empty] | 0
User Story 32 - RF14.2.6 | Team Member Name | [21 empty] | 0
User Story 33 - RF14.3 | Team Member Name | [21 empty] | 0
User Story 33 - RF14.3.1 | Team Member Name | [21 empty] | 0
User Story 33 - RF14.3.2 | Team Member Name | [21 empty] | 0
User Story 33 - RF14.3.3 | Team Member Name | [21 empty] | 0
User Story 33 - RF14.3.4 | Team Member Name | [21 empty] | 0
User Story 33 - RF14.3.5 | Team Member Name | [21 empty] | 0
User Story 33 - RF14.3.6 | Team Member Name | [21 empty] | 0
User Story 33 - RF14.3.7 | Team Member Name | [21 empty] | 0
User Story 33 - RF14.3.8 | Team Member Name | [21 empty] | 0
User Story 33 - RF14.3.9 | Team Member Name | [21 empty] | 0
User Story 33 - RF14.3.10 | Team Member Name | [21 empty] | 0
User Story 34 - RF15.1 | Team Member Name | [21 empty] | 0
User Story 34 - RF15.1.1 | Team Member Name | [21 empty] | 0
User Story 34 - RF15.1.2 | Team Member Name | [21 empty] | 0
User Story 34 - RF15.1.3 | Team Member Name | [21 empty] | 0
User Story 34 - RF15.1.4 | Team Member Name | [21 empty] | 0
User Story 34 - RF15.1.5 | Team Member Name | [21 empty] | 0
User Story 34 - RF15.1.6 | Team Member Name | [21 empty] | 0
User Story 35 - RF15.2 | Team Member Name | [21 empty] | 0
User Story 35 - RF15.2.1 | Team Member Name | [21 empty] | 0
User Story 35 - RF15.2.2 | Team Member Name | [21 empty] | 0
User Story 35 - RF15.2.3 | Team Member Name | [21 empty] | 0
User Story 36 - RF15.2.4 | Team Member Name | [21 empty] | 0
User Story 37 - RF21.1 | Team Member Name | [21 empty] | 0
User Story 37 - RF21.2 | Team Member Name | [21 empty] | 0
User Story 37 - RF21.3 | Team Member Name | [21 empty] | 0
|  | 112 | 103 | 83 | 32 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Ideal Trend |  | 112 | 84 | 56 | 28 | 0 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
Note on H4: For an Accurate Burndown Chart and Ideal Trend, Fill in the expected working days in an Iteration (1 Week = 5 Days). You can additionally choose to hide columns that are not needed. If your Iteration is 2 weeks long, you can hide columns M through V and place 10 in this box. Default Formula Assumes 20 days

## Sprint 5
1
Iteration Number:
|  |  | Expected Total effort: |  |  |  | 224
|  |  | Days In Sprint: |  |  |  | 8
Burndown Chart
User Stories |  |  | Days (Points Completed) | [19 empty] | Remaining
Sprint Backlog Items | Done by | Beginning Balance | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | Task Balance | Percentage Completed
User Story 2 - RF1.3 | Team Member Name | 0 | [20 empty] | 0
User Story 2 - RF1.4 | Team Member Name | 0 | [20 empty] | 0
User Story 3 - RF1.5 | Team Member Name | 0 | [20 empty] | 0
User Story 4 - RF1.7 | Team Member Name | 2 | [20 empty] | 0 | 100% | bar: Days (Points Completed) 1; Days (Points Completed) 4
User Story 7 - RF2.7 | Team Member Name | [21 empty] | 0
User Story 8 - RF2.8 | Team Member Name | [21 empty] | 0
User Story 10 - RF3.1 | Team Member Name | 1 | [20 empty] | 0 | bar: Days (Points Completed) 1
User Story 10 - RF3.2 | Team Member Name | 1 | [20 empty] | 0 | bar: Days (Points Completed) 2
User Story 10 - RF3.3 | Team Member Name | 2 | [20 empty] | 0 | bar: Days (Points Completed) 2; Days (Points Completed) 4
User Story 10 - RF3.4 | Team Member Name | 1 | [20 empty] | 0 | bar: Days (Points Completed) 4
User Story 10 - RF4.1 | Team Member Name | 2 | [20 empty] | 0 | bar: Days (Points Completed) 1; Days (Points Completed) 5
User Story 10 - RF4.2 | Team Member Name | 1 | [20 empty] | 0 | bar: Days (Points Completed) 3
User Story 10 - RF4.3 | Team Member Name | 2 | [20 empty] | 0 | bar: Days (Points Completed) 3; Days (Points Completed) 5
User Story 10 - RF4.4 | Team Member Name | 1 | [20 empty] | 0 | bar: Days (Points Completed) 4
User Story 10 - RF4.5 | Team Member Name | 2 | [20 empty] | 0 | bar: Days (Points Completed) 1; Days (Points Completed) 3
User Story 10 - RF5.1 | Team Member Name | 1 | [20 empty] | 0 | bar: Days (Points Completed) 2
User Story 10 - RF5.2 | Team Member Name | 2 | [20 empty] | 0 | bar: Days (Points Completed) 2; Days (Points Completed) 5
User Story 10 - RF5.3 | Team Member Name | 1 | [20 empty] | 0 | bar: Days (Points Completed) 5
User Story 10 - RF5.4 | Team Member Name | 1 | [20 empty] | -1 | bar: Days (Points Completed) 2; Days (Points Completed) 5
User Story 10 - RF6.1 | Team Member Name | 1 | [20 empty] | 0 | bar: Days (Points Completed) 1
User Story 10 - RF6.2 | Team Member Name | 2 | [20 empty] | 0 | bar: Days (Points Completed) 4 to Days (Points Completed) 5
User Story 10 - RF6.3 | Team Member Name | 2 | [20 empty] | 0 | bar: Days (Points Completed) 1 to Days (Points Completed) 2
User Story 10 - RF6.4 | Team Member Name | 1 | [20 empty] | -1 | bar: Days (Points Completed) 2 to Days (Points Completed) 3
User Story 11 - RF17.1 | Team Member Name | 1 | [20 empty] | 0 | bar: Days (Points Completed) 4
User Story 11 - RF17.2 | Team Member Name | 1 | [20 empty] | 0 | bar: Days (Points Completed) 5
User Story 11 - RF17.3 | Team Member Name | 1 | [20 empty] | 0 | bar: Days (Points Completed) 3
User Story 11 - RF17.4 | Team Member Name | 1 | [20 empty] | 0 | bar: Days (Points Completed) 2
User Story 12 - RF7.1 | Team Member Name | 1 | [20 empty] | 0 | bar: Days (Points Completed) 3
User Story 12 - RF7.4 | Team Member Name | 2 | [20 empty] | 0 | bar: Days (Points Completed) 4 to Days (Points Completed) 5
User Story 13 - RF7.2 | Team Member Name | 2 | [20 empty] | 0 | bar: Days (Points Completed) 3 to Days (Points Completed) 4
User Story 13 - RF7.3 | Team Member Name | 1 | [20 empty] | 0 | bar: Days (Points Completed) 4
User Story 14 - RF19.1 | Team Member Name | 2 | [20 empty] | 0 | bar: Days (Points Completed) 2; Days (Points Completed) 4
User Story 14 - RF19.2 | Team Member Name | 1 | [20 empty] | 0 | bar: Days (Points Completed) 2
User Story 14 - RF19.3 | Team Member Name | 2 | [20 empty] | 0 | bar: Days (Points Completed) 1; Days (Points Completed) 3
User Story 14 - RF19.4 | Team Member Name | 1 | [20 empty] | 0 | bar: Days (Points Completed) 1
User Story 15 - RF18.1 | Team Member Name | 1 | [20 empty] | 0 | bar: Days (Points Completed) 2
User Story 15 - RF18.2 | Team Member Name | 1 | [20 empty] | 0 | bar: Days (Points Completed) 3
User Story 15 - RF18.3 | Team Member Name | 1 | [20 empty] | 0 | bar: Days (Points Completed) 4
User Story 15 - RF18.4 | Team Member Name | 2 | [20 empty] | 0 | bar: Days (Points Completed) 4 to Days (Points Completed) 5
User Story 16 - RF20.1 | Team Member Name | 1 | [20 empty] | 0 | bar: Days (Points Completed) 3
User Story 16 - RF20.2 | Team Member Name | 2 | [20 empty] | 0 | bar: Days (Points Completed) 2 to Days (Points Completed) 3
User Story 16 - RF20.3 | Team Member Name | 2 | [20 empty] | 0 | bar: Days (Points Completed) 3 to Days (Points Completed) 4
User Story 16 - RF20.4 | Team Member Name | 2 | [20 empty] | 0 | bar: Days (Points Completed) 4 to Days (Points Completed) 5
User Story 17 - RF20.5 | Team Member Name | [21 empty] | 0
User Story 17 - RF20.7 | Team Member Name | [21 empty] | 0
User Story 18 - RF20.6 | Team Member Name | [21 empty] | 0
User Story 19 - RF8.1 | Team Member Name | [21 empty] | 0
User Story 19 - RF8.2 | Team Member Name | [21 empty] | 0
User Story 19 - RF8.3 | Team Member Name | 2 | [20 empty] | 0 | bar: Days (Points Completed) 1 to Days (Points Completed) 2
User Story 19 - RF8.4 | Team Member Name | 2 | [20 empty] | 0 | bar: Days (Points Completed) 2 to Days (Points Completed) 3
User Story 20 - RF9.1 | Team Member Name | 1 | [20 empty] | 0 | bar: Days (Points Completed) 3
User Story 21 - RF9.4 | Team Member Name | 2 | [20 empty] | 0 | bar: Days (Points Completed) 3 to Days (Points Completed) 4
User Story 22 - RF9.2 | Team Member Name | 1 | [20 empty] | 0 | bar: Days (Points Completed) 5
User Story 22 - RF9.3 | Team Member Name | 1 | [20 empty] | 0 | bar: Days (Points Completed) 5
User Story 23 - RF10.1 | Team Member Name | 2 | [20 empty] | 0 | bar: Days (Points Completed) 4 to Days (Points Completed) 5
User Story 23 - RF10.2 | Team Member Name | 2 | [20 empty] | 0 | bar: Days (Points Completed) 2 to Days (Points Completed) 3
User Story 23 - RF10.3 | Team Member Name | 2 | [20 empty] | 0 | bar: Days (Points Completed) 2 to Days (Points Completed) 3
User Story 23 - RF10.4 | Team Member Name | 1 | [20 empty] | 0 | bar: Days (Points Completed) 2
User Story 24 - RF11.1 | Team Member Name | [21 empty] | 0
User Story 24 - RF11.2 | Team Member Name | [21 empty] | 0
User Story 24 - RF11.3 | Team Member Name | [21 empty] | 0
User Story 24 - RF11.4 | Team Member Name | [21 empty] | 0
User Story 24 - RF11.5 | Team Member Name | [21 empty] | 0
User Story 24 - RF11.6 | Team Member Name | [21 empty] | 0
User Story 24 - RF11.7 | Team Member Name | [21 empty] | 0
User Story 25 - RF12.1 | Team Member Name | 1 | [20 empty] | 0 | bar: Days (Points Completed) 2
User Story 26 - RF12.1 | Team Member Name | 1 | [20 empty] | 0 | bar: Days (Points Completed) 2
User Story 26 - RF12.2 | Team Member Name | 1 | [20 empty] | 0 | bar: Days (Points Completed) 3
User Story 26 - RF12.3 | Team Member Name | 1 | [20 empty] | 0 | bar: Days (Points Completed) 3
User Story 26 - RF12.4 | Team Member Name | 2 | [20 empty] | 0 | bar: Days (Points Completed) 4 to Days (Points Completed) 5
User Story 27 - RF13.1 | Team Member Name | 1 | [20 empty] | 0 | bar: Days (Points Completed) 4
User Story 28 - RF13.2 | Team Member Name | 1 | [20 empty] | 0 | bar: Days (Points Completed) 3
User Story 28 - RF13.3 | Team Member Name | 1 | [20 empty] | 0 | bar: Days (Points Completed) 2
User Story 28 - RF13.5 | Team Member Name | 2 | [20 empty] | 0 | bar: Days (Points Completed) 2 to Days (Points Completed) 3
User Story 28 - RF13.6 | Team Member Name | 2 | [20 empty] | 0 | bar: Days (Points Completed) 2; Days (Points Completed) 4
User Story 29 - RF13.4 | Team Member Name | 2 | [20 empty] | 0 | bar: Days (Points Completed) 2 to Days (Points Completed) 3
User Story 30 - RF14.1 | Team Member Name | 1 | [20 empty] | 0 | bar: Days (Points Completed) 3
User Story 31 - RF14.1.1 | Team Member Name | 2 | [20 empty] | 0 | bar: Days (Points Completed) 2; Days (Points Completed) 4
User Story 31 - RF14.1.2 | Team Member Name | 1 | [20 empty] | 0 | bar: Days (Points Completed) 1
User Story 31 - RF14.1.3 | Team Member Name | 1 | [20 empty] | 0 | bar: Days (Points Completed) 2
User Story 31 - RF14.1.5 | Team Member Name | 2 | [20 empty] | 0 | bar: Days (Points Completed) 1 to Days (Points Completed) 2
User Story 31 - RF14.1.6 | Team Member Name | 2 | [20 empty] | 0 | bar: Days (Points Completed) 2 to Days (Points Completed) 3
User Story 32 - RF14.2 | Team Member Name | 1 | Days (Points Completed) 1: 1; Days (Points Completed) 3: 0 | 0
User Story 32 - RF14.2.1 | Team Member Name | 1 | [20 empty] | 0 | bar: Days (Points Completed) 3
User Story 32 - RF14.2.2 | Team Member Name | 1 | [20 empty] | 0 | bar: Days (Points Completed) 3
User Story 32 - RF14.2.3 | Team Member Name | 2 | [20 empty] | 0 | bar: Days (Points Completed) 4 to Days (Points Completed) 5
User Story 32 - RF14.2.4 | Team Member Name | 2 | [20 empty] | 0 | bar: Days (Points Completed) 1; Days (Points Completed) 4
User Story 32 - RF14.2.5 | Team Member Name | 2 | Days (Points Completed) 1: 2 | 0
User Story 32 - RF14.2.6 | Team Member Name | 1 | [20 empty] | 0 | bar: Days (Points Completed) 5
User Story 33 - RF14.3 | Team Member Name | 1 | [20 empty] | 0 | bar: Days (Points Completed) 1
User Story 33 - RF14.3.1 | Team Member Name | 1 | [20 empty] | 0 | bar: Days (Points Completed) 3
User Story 33 - RF14.3.2 | Team Member Name | 2 | Days (Points Completed) 4: 2 | 0
User Story 33 - RF14.3.3 | Team Member Name | 1 | Days (Points Completed) 1: 2 | -1
User Story 33 - RF14.3.4 | Team Member Name | 2 | Days (Points Completed) 5: 2 | 0
User Story 33 - RF14.3.5 | Team Member Name | 2 | Days (Points Completed) 1: 2 | 0
User Story 33 - RF14.3.6 | Team Member Name | 2 | [20 empty] | 0 | bar: Days (Points Completed) 2; Days (Points Completed) 4
User Story 33 - RF14.3.7 | Team Member Name | 2 | Days (Points Completed) 3: 1; Days (Points Completed) 5: 2 | -1
User Story 33 - RF14.3.8 | Team Member Name | 1 | [20 empty] | 0 | bar: Days (Points Completed) 1
User Story 33 - RF14.3.9 | Team Member Name | 1 | [20 empty] | 0 | bar: Days (Points Completed) 1
User Story 33 - RF14.3.10 | Team Member Name | 1 | [20 empty] | 0 | bar: Days (Points Completed) 1
User Story 34 - RF15.1 | Team Member Name | 1 | [20 empty] | 0 | bar: Days (Points Completed) 1
User Story 34 - RF15.1.1 | Team Member Name | 1 | [20 empty] | 0 | bar: Days (Points Completed) 3
User Story 34 - RF15.1.2 | Team Member Name | 1 | [20 empty] | 0 | bar: Days (Points Completed) 4
User Story 34 - RF15.1.3 | Team Member Name | 2 | [20 empty] | 0 | bar: Days (Points Completed) 4 to Days (Points Completed) 5
User Story 34 - RF15.1.4 | Team Member Name | 2 | Days (Points Completed) 3: 2 | 0
User Story 34 - RF15.1.5 | Team Member Name | 1 | [20 empty] | 0 | bar: Days (Points Completed) 1
User Story 34 - RF15.1.6 | Team Member Name | 2 | [20 empty] | 0 | bar: Days (Points Completed) 2 to Days (Points Completed) 3
User Story 35 - RF15.2 | Team Member Name | 1 | [20 empty] | 0 | bar: Days (Points Completed) 3
User Story 35 - RF15.2.1 | Team Member Name | 1 | [20 empty] | 0 | bar: Days (Points Completed) 4
User Story 35 - RF15.2.2 | Team Member Name | 2 | Days (Points Completed) 5: 2 | 0
User Story 35 - RF15.2.3 | Team Member Name | 2 | Days (Points Completed) 5: 2 | 0
User Story 36 - RF15.2.4 | Team Member Name | 1 | [20 empty] | 0 | bar: Days (Points Completed) 2
User Story 37 - RF21.1 | Team Member Name | 1 | [20 empty] | 0 | bar: Days (Points Completed) 1
User Story 37 - RF21.2 | Team Member Name | 1 | [20 empty] | 0 | bar: Days (Points Completed) 2
User Story 37 - RF21.3 | Team Member Name | 1 | [20 empty] | 0 | bar: Days (Points Completed) 2
|  | 224 | 198 | 166 | 133 | 105 | 80 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Ideal Trend |  | 224 | 196 | 168 | 140 | 112 | 84 | 56 | 28 | 0 | - | - | - | - | - | - | - | - | - | - | - | - | -
Note on H4: For an Accurate Burndown Chart and Ideal Trend, Fill in the expected working days in an Iteration (1 Week = 5 Days). You can additionally choose to hide columns that are not needed. If your Iteration is 2 weeks long, you can hide columns M through V and place 10 in this box. Default Formula Assumes 20 days

## total
Iteration Number:
|  |  | Expected Total effort: |  |  |  | 560
|  |  | Days In Sprint: |  |  |  | 20
Burndown Chart
User Stories |  |  | Days (Points Completed) | [19 empty] | Remaining
Sprint Backlog Items | Done by | Beginning Balance | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | Task Balance | Percentage Completed
User Story 1 - RF1.1 | Team Member Name | 6 | Days (Points Completed) 1: 3; Days (Points Completed) 2: 3 | 0 | 100% | 1
User Story 1 - RF1.2 | Team Member Name | 6 | Days (Points Completed) 1: 3; Days (Points Completed) 2: 3 | 0 | 100% | 1
User Story 1 - RF1.6 | Team Member Name | 5 | Days (Points Completed) 1: 3; Days (Points Completed) 2: 2 | 0 | 100% | 1
User Story 5 - RF2.1 | Team Member Name | 5 | Days (Points Completed) 2: 1; Days (Points Completed) 3: 4 | 0 | 100% | 1
User Story 5 - RF2.2 | Team Member Name | 5 | Days (Points Completed) 3: 1; Days (Points Completed) 4: 4 | 0 | 100% | 1
User Story 5 - RF2.3 | Team Member Name | 5 | Days (Points Completed) 3: 2; Days (Points Completed) 4: 3 | 0 | 100% | 1
User Story 5 - RF2.4 | Team Member Name | 5 | Days (Points Completed) 2: 1; Days (Points Completed) 3: 4 | 0 | 100% | 1
User Story 5 - RF2.5 | Team Member Name | 5 | Days (Points Completed) 2: 2; Days (Points Completed) 3: 1; Days (Points Completed) 4: 2 | 0 | 100% | 1
User Story 5 - RF2.6 | Team Member Name | 5 | Days (Points Completed) 2: 1; Days (Points Completed) 3: 1; Days (Points Completed) 4: 3 | 0 | 100% | 1
User Story 6 - RF2.2 | Team Member Name | 5 | Days (Points Completed) 2: 1; Days (Points Completed) 3: 4 | 0 | 100% | 1
User Story 6 - RF2.3 | Team Member Name | 5 | Days (Points Completed) 2: 2; Days (Points Completed) 3: 1; Days (Points Completed) 4: 2 | 0 | 100% | 1
User Story 6 - RF2.4 | Team Member Name | 5 | Days (Points Completed) 2: 1; Days (Points Completed) 3: 1; Days (Points Completed) 4: 3 | 0 | 100% | 1
User Story 6 - RF2.5 | Team Member Name | 5 | Days (Points Completed) 2: 1; Days (Points Completed) 3: 4 | 0 | 100% | 1
User Story 6 - RF2.6 | Team Member Name | 5 | Days (Points Completed) 2: 2; Days (Points Completed) 3: 2; Days (Points Completed) 4: 1 | 0 | 100% | 1
User Story 9 - RF16.1 | Team Member Name | 5 | Days (Points Completed) 3: 5 | 0 | 100% | 1
User Story 9 - RF16.2 | Team Member Name | 5 | Days (Points Completed) 3: 2; Days (Points Completed) 4: 3 | 0 | 100% | 1
User Story 9 - RF16.3 | Team Member Name | 5 | Days (Points Completed) 3: 2; Days (Points Completed) 4: 3 | 0 | 100% | 1
User Story 9 - RF16.4 | Team Member Name | 5 | Days (Points Completed) 3: 5 | 0 | 100% | 1
User Story 9 - RF16.5 | Team Member Name | 5 | Days (Points Completed) 3: 3; Days (Points Completed) 4: 2 | 0 | 100% | 1
User Story 9 - RF16.7 | Team Member Name | 5 | Days (Points Completed) 3: 2; Days (Points Completed) 4: 3 | 0 | 100% | 1
User Story 9 - RF16.8 | Team Member Name | 5 | Days (Points Completed) 3: 5; Days (Points Completed) 4: 0 | 0 | 100% | 1
User Story 9 - RF16.9 | Team Member Name | 5 | Days (Points Completed) 3: 2; Days (Points Completed) 4: 3 | 0 | 100% | 1
User Story 2 - RF1.3 | Team Member Name | 0 | [20 empty] | 0
User Story 2 - RF1.4 | Team Member Name | 0 | [20 empty] | 0
User Story 3 - RF1.5 | Team Member Name | 0 | [20 empty] | 0
User Story 4 - RF1.7 | Team Member Name | 0 | [20 empty] | 0
User Story 7 - RF2.7 | Team Member Name | [21 empty] | 0
User Story 8 - RF2.8 | Team Member Name | [21 empty] | 0
User Story 10 - RF3.1 | Team Member Name | [21 empty] | 0
User Story 10 - RF3.2 | Team Member Name | [21 empty] | 0
User Story 10 - RF3.3 | Team Member Name | [21 empty] | 0
User Story 10 - RF3.4 | Team Member Name | [21 empty] | 0
User Story 10 - RF4.1 | Team Member Name | [21 empty] | 0
User Story 10 - RF4.2 | Team Member Name | [21 empty] | 0
User Story 10 - RF4.3 | Team Member Name | [21 empty] | 0
User Story 10 - RF4.4 | Team Member Name | [21 empty] | 0
User Story 10 - RF4.5 | Team Member Name | [21 empty] | 0
User Story 10 - RF5.1 | Team Member Name | [21 empty] | 0
User Story 10 - RF5.2 | Team Member Name | [21 empty] | 0
User Story 10 - RF5.3 | Team Member Name | [21 empty] | 0
User Story 10 - RF5.4 | Team Member Name | [21 empty] | 0
User Story 10 - RF6.1 | Team Member Name | [21 empty] | 0
User Story 10 - RF6.2 | Team Member Name | [21 empty] | 0
User Story 10 - RF6.3 | Team Member Name | [21 empty] | 0
User Story 10 - RF6.4 | Team Member Name | [21 empty] | 0
User Story 11 - RF17.1 | Team Member Name | [21 empty] | 0
User Story 11 - RF17.2 | Team Member Name | [21 empty] | 0
User Story 11 - RF17.3 | Team Member Name | [21 empty] | 0
User Story 11 - RF17.4 | Team Member Name | [21 empty] | 0
User Story 12 - RF7.1 | Team Member Name | [21 empty] | 0
User Story 12 - RF7.4 | Team Member Name | [21 empty] | 0
User Story 13 - RF7.2 | Team Member Name | [21 empty] | 0
User Story 13 - RF7.3 | Team Member Name | [21 empty] | 0
User Story 14 - RF19.1 | Team Member Name | [21 empty] | 0
User Story 14 - RF19.2 | Team Member Name | [21 empty] | 0
User Story 14 - RF19.3 | Team Member Name | [21 empty] | 0
User Story 14 - RF19.4 | Team Member Name | [21 empty] | 0
User Story 15 - RF18.1 | Team Member Name | [21 empty] | 0
User Story 15 - RF18.2 | Team Member Name | [21 empty] | 0
User Story 15 - RF18.3 | Team Member Name | [21 empty] | 0
User Story 15 - RF18.4 | Team Member Name | [21 empty] | 0
User Story 16 - RF20.1 | Team Member Name | [21 empty] | 0
User Story 16 - RF20.2 | Team Member Name | [21 empty] | 0
User Story 16 - RF20.3 | Team Member Name | [21 empty] | 0
User Story 16 - RF20.4 | Team Member Name | [21 empty] | 0
User Story 17 - RF20.5 | Team Member Name | [21 empty] | 0
User Story 17 - RF20.7 | Team Member Name | [21 empty] | 0
User Story 18 - RF20.6 | Team Member Name | [21 empty] | 0
User Story 19 - RF8.1 | Team Member Name | [21 empty] | 0
User Story 19 - RF8.2 | Team Member Name | [21 empty] | 0
User Story 19 - RF8.3 | Team Member Name | [21 empty] | 0
User Story 19 - RF8.4 | Team Member Name | [21 empty] | 0
User Story 20 - RF9.1 | Team Member Name | [21 empty] | 0
User Story 21 - RF9.4 | Team Member Name | [21 empty] | 0
User Story 22 - RF9.2 | Team Member Name | [21 empty] | 0
User Story 22 - RF9.3 | Team Member Name | [21 empty] | 0
User Story 23 - RF10.1 | Team Member Name | [21 empty] | 0
User Story 23 - RF10.2 | Team Member Name | [21 empty] | 0
User Story 23 - RF10.3 | Team Member Name | [21 empty] | 0
User Story 23 - RF10.4 | Team Member Name | [21 empty] | 0
User Story 24 - RF11.1 | Team Member Name | [21 empty] | 0
User Story 24 - RF11.2 | Team Member Name | [21 empty] | 0
User Story 24 - RF11.3 | Team Member Name | [21 empty] | 0
User Story 24 - RF11.4 | Team Member Name | [21 empty] | 0
User Story 24 - RF11.5 | Team Member Name | [21 empty] | 0
User Story 24 - RF11.6 | Team Member Name | [21 empty] | 0
User Story 24 - RF11.7 | Team Member Name | [21 empty] | 0
User Story 25 - RF12.1 | Team Member Name | [21 empty] | 0
User Story 26 - RF12.1 | Team Member Name | [21 empty] | 0
User Story 26 - RF12.2 | Team Member Name | [21 empty] | 0
User Story 26 - RF12.3 | Team Member Name | [21 empty] | 0
User Story 26 - RF12.4 | Team Member Name | [21 empty] | 0
User Story 27 - RF13.1 | Team Member Name | [21 empty] | 0
User Story 28 - RF13.2 | Team Member Name | [21 empty] | 0
User Story 28 - RF13.3 | Team Member Name | [21 empty] | 0
User Story 28 - RF13.5 | Team Member Name | [21 empty] | 0
User Story 28 - RF13.6 | Team Member Name | [21 empty] | 0
User Story 29 - RF13.4 | Team Member Name | [21 empty] | 0
User Story 30 - RF14.1 | Team Member Name | [21 empty] | 0
User Story 31 - RF14.1.1 | Team Member Name | [21 empty] | 0
User Story 31 - RF14.1.2 | Team Member Name | [21 empty] | 0
User Story 31 - RF14.1.3 | Team Member Name | [21 empty] | 0
User Story 31 - RF14.1.5 | Team Member Name | [21 empty] | 0
User Story 31 - RF14.1.6 | Team Member Name | [21 empty] | 0
User Story 32 - RF14.2 | Team Member Name | [21 empty] | 0
User Story 32 - RF14.2.1 | Team Member Name | [21 empty] | 0
User Story 32 - RF14.2.2 | Team Member Name | [21 empty] | 0
User Story 32 - RF14.2.3 | Team Member Name | [21 empty] | 0
User Story 32 - RF14.2.4 | Team Member Name | [21 empty] | 0
User Story 32 - RF14.2.5 | Team Member Name | [21 empty] | 0
User Story 32 - RF14.2.6 | Team Member Name | [21 empty] | 0
User Story 33 - RF14.3 | Team Member Name | [21 empty] | 0
User Story 33 - RF14.3.1 | Team Member Name | [21 empty] | 0
User Story 33 - RF14.3.2 | Team Member Name | [21 empty] | 0
User Story 33 - RF14.3.3 | Team Member Name | [21 empty] | 0
User Story 33 - RF14.3.4 | Team Member Name | [21 empty] | 0
User Story 33 - RF14.3.5 | Team Member Name | [21 empty] | 0
User Story 33 - RF14.3.6 | Team Member Name | [21 empty] | 0
User Story 33 - RF14.3.7 | Team Member Name | [21 empty] | 0
User Story 33 - RF14.3.8 | Team Member Name | [21 empty] | 0
User Story 33 - RF14.3.9 | Team Member Name | [21 empty] | 0
User Story 33 - RF14.3.10 | Team Member Name | [21 empty] | 0
User Story 34 - RF15.1 | Team Member Name | [21 empty] | 0
User Story 34 - RF15.1.1 | Team Member Name | [21 empty] | 0
User Story 34 - RF15.1.2 | Team Member Name | [21 empty] | 0
User Story 34 - RF15.1.3 | Team Member Name | [21 empty] | 0
User Story 34 - RF15.1.4 | Team Member Name | [21 empty] | 0
User Story 34 - RF15.1.5 | Team Member Name | [21 empty] | 0
User Story 34 - RF15.1.6 | Team Member Name | [21 empty] | 0
User Story 35 - RF15.2 | Team Member Name | [21 empty] | 0
User Story 35 - RF15.2.1 | Team Member Name | [21 empty] | 0
User Story 35 - RF15.2.2 | Team Member Name | [21 empty] | 0
User Story 35 - RF15.2.3 | Team Member Name | [21 empty] | 0
User Story 36 - RF15.2.4 | Team Member Name | [21 empty] | 0
User Story 37 - RF21.1 | Team Member Name | [21 empty] | 0
User Story 37 - RF21.2 | Team Member Name | [21 empty] | 0
User Story 37 - RF21.3 | Team Member Name | [21 empty] | 0
|  | 560 | 551 | 531 | 480 | 448 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Ideal Trend |  | 560 | 532 | 504 | 476 | 448 | 420 | 392 | 364 | 336 | 308 | 280 | 252 | 224 | 196 | 168 | 140 | 112 | 84 | 56 | 28 | 0 | -
Note on H4: For an Accurate Burndown Chart and Ideal Trend, Fill in the expected working days in an Iteration (1 Week = 5 Days). You can additionally choose to hide columns that are not needed. If your Iteration is 2 weeks long, you can hide columns M through V and place 10 in this box. Default Formula Assumes 20 days

## Folha1
16 | dias
4 | pessoas
7 | horas
448
5